## Defect Tracking log
DEFECT TRACKING LOG
Project Name | Trainer Managment System
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
Defect No. | Date Created | Created By | Defect Description | Steps to replicate issue | Expected | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause
1 | 2022-08-15 | Vysakh | ICTAK Courses handling drop down not set to mandatory on Sign Up | Open sign up link, fill all fields with valid inputs and leave Course field blank. Sign Up button enabled even with this field blank | Sign Up button should be active only after all fields have valid data | Executing/Controlling | Testing | Low | Dev Team | 2022-08-15 |  | In Progress
3 | 2022-08-17 | Vysakh | No restriction blocking multiple registration with same mail id | Sign Up twice using same information | Should not complete sign up if trainer already registered and approved | Executing/Controlling | Testing | Medium | Dev Team | 2022-08-17 |  | In Progress
4 | 2022-08-17 | Vysakh | Incase of multiple registration with same mail id, system maintains data of first approval but generates new trainer ID on approval by admin | Sign Up twice using same information | Should not complete sign up if trainer already registered and approved | Executing/Controlling | Testing | High | Dev Team | 2022-08-17 |  | In Progress
5 | 2022-08-17 | Vysakh | Trainer Search using Employment type not possible as TYPE is not shown on Allocate page | Login using admin credentials and view "Allocation" list, check for Type column | As per REQ4, Admin should be able to Search trainer based on employment type | Executing/Controlling | Testing | Medium | Dev Team | 2022-08-17 |  | In Progress
6 | 2022-08-17 | Vysakh | Functionality to block calendar after allocation of trainer not implemented | Login using admin credentials and schedule a training for a Trainer from the list, and then schedule a different course training for the same trainer on same date and time | Trainer allocation should not be permitted as there is a schedule conflict | Executing/Controlling | Testing | High | Dev Team | 2022-08-17 |  | In Progress
7 | 2022-08-19 | Remya | After editing profile, have to refresh page most times to see saved data | Login using trainer credentials, Edit profile data, click on Edit to save to get back to Trainer profile page. | Information on Trainer profile needs to be updated automatically and should not require a page refresh | Executing/Controlling | Testing | Medium | Dev Team | 2022-08-19 |  | In Progress
8 | 2022-08-19 | Ayana | Trainer Approval, Trainer list, View Allocation pages take considerable time to load | Login using admin credentials, click on Allocate, ViewAllocation menus. Each page takes considerable time to load data | Loading time of each of these pages need to be less than 2seconds for optimal user experience | Executing/Controlling | Testing | Medium | Dev Team | 2022-08-19 |  | In Progress
9 | 2022-08-29 | Vysakh | The table on "Allocate" page is not fully visibile in any browser resolution, part of the table border left/right is always cut off | Login using admin credentials, click on Allocate, the right edge of table has an overlay | Table borders and content should be fully visible | Executing/Controlling | Testing | Low | Dev Team | 2022-08-29 |  | In Progress
10 | 2022-08-29 | Vysakh | In Trainer profile edit page, the button needs to say "Save" instead of Edit | Login using trainer credentials, Edit profile data, it would be more meaningful for the button to say Save | Button inside the edit profile page needs to be labelled Save | Executing/Controlling | Testing | Low | Dev Team | 2022-08-29 |  | In Progress
11 | 2022-08-29 | Vysakh | Employment Type drop down in admin dashboard not set to mandatory | Login using admin credentials, Approve option works even without selecting employment type | Employment type drop down on Admin dashboard needs to be mandatory | Executing/Controlling | Testing | Medium | Dev Team | 2022-08-29 |  | In Progress
12 | 2022-09-03 | Vysakh | Editing email address in Trainer profile changes the Website login also | Login using trainer credentials, Edit profile and change email address, Save and logout and then try to login again with initial registration mail id | Email used at the time of registration needs to be the permanent login username of the trainer | Executing/Controlling | Testing | Medium | Dev Team | 2022-09-03 |  | In Progress
13 | 2022-09-07 | Vysakh | Resizing browser window cuts off portion of the table with no veritical or horizontal scroll bars, Only the menu on top adapts to window resize | Login using admin credentials, open Allocate, View Allocation or Admin dashboard. Resize browser window | Horizontal and Vertical scroll bars need to be provided when browser window size does not allow full view of the tables | Executing/Controlling | Testing | Medium | Dev Team | 2022-09-07 |  | In Progress